## Overview
AqOne Year 1 Plan: DOST-Funded Pilot Deliverables
What we deliver in the 12-month DOST grant period: building, deployment, a 6-month validation period, training for fishers and MDRRMO, and promotion. All dates follow the start date below.
| Status | DRAFT (for team and ASU review)
| Owner | Aquanons (Lenard, lead student researcher)
| Created / Updated | 2026-09-30
| Related | docs/funding/Aquanons_Master_Budget.xlsx, AqOne_Investor_Model.xlsx, AqOne_Handoff_Doreen.md
PROJECT DATES
| Official DOST start date (Month 1) | 2027-01-01 |  | ASSUMPTION: January 2027. Change this cell when DOST confirms; every date in the workbook updates.
| End of grant period (Month 12) | 2027-12-31
| Validation period (Months 7-12) | Jul 1, 2027 to Dec 31, 2027 |  | Six months of supported SOS operation, measured against the validation protocol.
| Grant amount requested | 1705525.37 |  | From Aquanons_Master_Budget.xlsx (28 Sep 2026). See Budget Notes for costs this plan adds.
THREE PHASES
| Phase | Starts | Ends | Goal
| 1. Set up and build | 2027-01-01 | 2027-03-31 | Agreements, procurement, firmware, app, dashboard and devices ready; validation protocol approved; community awareness starts.
| 2. Deploy, train and commission | 2027-04-01 | 2027-06-30 | Coverage measured, devices installed, MDRRMO and fishers trained, soft launch, SOS acceptance test passed (go-live).
| 3. Validation period | 2027-07-01 | 2027-12-31 | Six months of supported SOS operation with scheduled and unannounced drills, surveys, usability tests, refresher training, launch and promotion, Year 2 commitment, final reports and handover.
WORKSTREAMS
| Workstream | Items | Lead | What it covers
| Setup | 3 | Doreen + faculty leader | Agreements, procurement, consent and privacy forms.
| Build | 5 | Lenard, Daniel, Jade, Arnold | Backend, firmware, app, dashboard, device assembly.
| Deploy | 2 | Daniel | Installation and onboarding of the 20 boats.
| Validation | 13 | Lenard | Protocol, coverage, soft launch, acceptance test, usability tests, unannounced and night drills, reviews, AI evaluation.
| Training | 10 | Doreen (fishers), Arnold (MDRRMO) | Curriculum, SOP, MDRRMO operators, champion fishers, fisher batches, joint exercise, refreshers, LGU technicians.
| Promotion | 14 | Doreen, KC | Communication kit, Facebook page, barangay assemblies, IEC materials, launch, media, stories, briefings, neighbouring LGUs, results forum.
| Operations | 2 | Daniel | The six-month validation period and the handover package.
| Reporting | 6 | Faculty leader | Quarterly reports, cost report, final report.
| Year 2 | 2 | Doreen, KC | Year 2 proposal and commitment from New Washington.
GATES: STOP-AND-CHECK POINTS
| Gate | Deadline | Decided by | If not met
| G1 Go/no-go on LGU agreement | 2027-02-28 | Faculty leader + Lenard | Switch to plan B: ASU-arranged boats, buoys and gateway sites, before installation.
| G2 Go-live | 2027-06-30 | Faculty leader, MDRRMO head, Lenard | Do not go live. Fix, re-test within 4 weeks, and shorten the validation period accordingly.
| G3 Investor Milestone 1 | 2027-12-31 | Investor, from DOST/ASU reports and logs | Investor may decline tranche 1 (₱3M).
TEAM
| Person | Role | Hours/week | Main Year 1 responsibilities
| Lenard | Lead student researcher: backend, architecture, deployment | 20 | Backend, validation protocol and reviews, SOP, acceptance test, AI evaluation, reports
| Daniel | Hardware and buoy firmware | 10 | Procurement, firmware, assembly, coverage, installation, upkeep, LGU technician training
| Jade | Flutter application | 10 | App, usability tests, fisher training (app parts)
| Arnold | Website dashboard | 10 | Dashboard, MDRRMO operator training, joint exercise
| Doreen Kay | Pitching, company branding, business direction | 10 | Promotion lead, fisher training lead, surveys, cost report, Year 2 commitment
| KC Condes | Pitching and business development support | 10 | Assemblies, IEC, media, surveys, neighbouring LGUs
| Faculty project leader (to be named) | Official DOST project leader |  | Approvals, procurement, gates, protocol, quarterly reports
Sheets: Deliverables (register) · Calendar (week by week) · Gantt · Training Plan · Validation Plan · Promotion Plan · Monthly Ops (validation period tracker) · Gates · Budget Notes (costs this plan adds). Yellow cells are inputs.

## Deliverables
Deliverables Register
Sorted by due month. Deadline = end of the due month. Filter by Workstream to see one area. Update Status and Date done as work finishes.
ID | Workstream | Deliverable | Starts (M) | Due (M) | Due date | Owner | Done when (pass/fail test) | Proof | Gate / milestone | Status | Date done | Notes
D1 | Build | Backend moved to paid Render plan | 1 | 1 | 2027-01-31 | Lenard | Paid database with backups live; staging copy live; uptime monitor on; one backup restore tested. | Render invoice, restore log |  | Not started
D2 | Setup | All pilot hardware ordered | 1 | 1 | 2027-01-31 | Daniel + faculty leader | Every B.1 item ordered through ASU procurement, with quotations attached. | Purchase orders, quotations |  | Not started
D3 | Setup | Fisher consent form and privacy notice | 1 | 1 | 2027-01-31 | Doreen | Consent form and privacy notice approved by the faculty leader, in English and Aklanon. | Approved forms |  | Not started
P1 | Promotion | Communication kit | 1 | 2 | 2027-02-28 | Doreen | Key messages in English, Filipino and Aklanon; logo and brand assets; photo/video consent form; one-page project explainer. | Kit folder |  | Not started
D4 | Setup | LGU agreement and MDRRMO commitment | 1 | 2 | 2027-02-28 | Doreen, KC + faculty leader | Signed MOA or LOI covering host buoys, boat access, 2 gateway sites and permits; MDRRMO agrees to monitor alerts and run drills. | Signed documents | G1 | Not started
D5 | Build | Firmware running on RAK boards | 1 | 3 | 2027-03-31 | Daniel | 100 of 100 bench SOS messages delivered pod → gateway → dashboard; pod battery lasts at least 48 h; recharge time measured. | Bench test log |  | Not started
D6 | Build | Android app ready (Google Play closed testing) | 1 | 3 | 2027-03-31 | Jade | SOS works through pod Wi-Fi with no internet; English, Filipino and Aklanon; runs on 5 low-end phones. | Play Console listing, phone test sheet |  | Not started
D7 | Build | MDRRMO dashboard ready | 1 | 3 | 2027-03-31 | Arnold | Operator receives and acknowledges a test SOS within 2 minutes; buoy, gateway and pod health visible. | Screen recording |  | Not started
V1 | Validation | Validation protocol approved | 2 | 3 | 2027-03-31 | Lenard + faculty leader | Written protocol: what we measure, targets, sample sizes, how data is collected, stored and anonymized; approved by the faculty leader. | Signed protocol |  | Not started
D8 | Build | All devices assembled and bench-tested | 2 | 3 | 2027-03-31 | Daniel + all | 3 buoy nodes, 22 pods and 2 gateways built; 72-hour burn-in and splash test passed. | Checklist with photos |  | Not started
R1 | Reporting | Quarterly report 1 | 3 | 3 | 2027-03-31 | Faculty leader, Lenard, Doreen | Technical and financial report submitted to ASU/DOST. | Submitted report |  | Not started
P8a | Promotion | Stakeholder briefing 1 | 3 | 3 | 2027-03-31 | Doreen, Lenard | Progress briefing to LGU, MDRRMO, BFAR and Coast Guard; questions and commitments recorded. | Attendance, notes |  | Not started
P3 | Promotion | Barangay assemblies in coastal barangays | 3 | 4 | 2027-04-30 | Doreen, KC + LGU | At least 4 assemblies held with the LGU; 20 boats signed up with a waitlist; common questions collected for the FAQ. | Attendance, sign-up list |  | Not started
D9 | Validation | Coverage map | 4 | 4 | 2027-04-30 | Daniel + Lenard | Signal measured at 50+ GPS-tagged points by boat; coverage map made; buoy positions confirmed with LGU and Coast Guard. | Coverage map and raw data |  | Not started
T1 | Training | Training curriculum and trainer guide | 4 | 5 | 2027-05-31 | Doreen, Jade | Modules, session plans, pre/post test and competency checklist for fishers and MDRRMO operators. | Curriculum, trainer guide |  | Not started
D10 | Training | Fisher training materials in Aklanon | 4 | 5 | 2027-05-31 | Doreen, KC, Jade | Handouts, picture guide and short videos on SOS, charging and basic checks; reviewed by the fisherfolk association. | Final materials, review notes |  | Not started
T2 | Training | SOS response procedure (SOP) signed with MDRRMO | 4 | 5 | 2027-05-31 | Lenard + faculty leader + MDRRMO | Written SOP: who acknowledges an SOS, target times, escalation to Coast Guard and BFAR, contact tree; signed off by the MDRRMO head. | Signed SOP | G2 | Not started
P4 | Promotion | IEC materials printed and placed | 5 | 5 | 2027-05-31 | Doreen, KC | Tarpaulins at the fish landing, port, barangay halls and MDRRMO; flyers in Aklanon distributed at assemblies. | Photos of placement |  | Not started
D11 | Deploy | Gateways and buoy nodes installed | 5 | 5 | 2027-05-31 | Daniel + all | 2 gateways on rooftops and 3 buoy nodes on host buoys, all reporting health for 7 days straight. | Dashboard logs, photos |  | Not started
T3 | Training | MDRRMO operator training | 6 | 6 | 2027-06-30 | Arnold, Lenard | All operators on the duty rota (at least 4) trained; each acknowledges a test SOS on the dashboard within 2 minutes; post-test score 80% or higher. | Attendance, test results | G2 | Not started
T4 | Training | Champion fisher training | 6 | 6 | 2027-06-30 | Doreen, Jade, Daniel | 5 respected fishers trained first as peer helpers; each can pair a pod, send SOS, charge and do basic checks, and explain them to others. | Attendance, competency checklist |  | Not started
V2 | Validation | Soft launch with 5 champion boats | 6 | 6 | 2027-06-30 | Lenard, Daniel | 5 boats use pods for 1 week before full rollout; at least 10 test messages each delivered; all issues found are fixed or logged. | Soft-launch log |  | Not started
V3 | Validation | Usability test round 1 | 6 | 6 | 2027-06-30 | Jade | At least 10 fishers each try: pair pod, send SOS, check battery. 90%+ complete each task without help; SOS sent within 60 seconds. | Test sheets, notes |  | Not started
T5 | Training | Fisher training batches and competency check | 6 | 6 | 2027-06-30 | Doreen, KC, Jade + champions | 3 batches covering all 20 boats (1-2 fishers per boat). Every fisher sends an SOS and charges a pod without help before receiving a pod; pre/post test gain recorded. | Attendance, competency sheets | G2 | Not started
D12 | Deploy | 20 boats onboarded | 6 | 6 | 2027-06-30 | Doreen, KC, Jade | 20 boats have pods; consent forms signed; pod serial numbers matched to boats in the dashboard. | Consent forms, device register | G2 | Not started
D13 | Validation | SOS acceptance test passed (go-live) | 6 | 6 | 2027-06-30 | Lenard, Daniel + MDRRMO | At least 30 drills at 3+ locations; 95%+ reach the dashboard within 2 min; MDRRMO acknowledges within 10 min; gateway power-loss and carrier-loss tests passed. | Drill report | G2, Milestone 1 | Not started
R2 | Reporting | Quarterly report 2 and mid-year review | 6 | 6 | 2027-06-30 | Faculty leader, Lenard, Doreen | Technical and financial report submitted; mid-year review held with ASU. | Submitted report |  | Not started
P8b | Promotion | Stakeholder briefing 2 | 6 | 6 | 2027-06-30 | Doreen, Lenard | Go-live readiness briefing to LGU, MDRRMO, BFAR and Coast Guard. | Attendance, notes |  | Not started
P5 | Promotion | Community launch and demo day | 7 | 7 | 2027-07-31 | Doreen, KC + LGU | Public launch with LGU, MDRRMO, Coast Guard, BFAR and ASU; live SOS demonstration; at least 60 attendees. | Program, photos, attendance |  | Not started
P6 | Promotion | Local media feature | 7 | 8 | 2027-08-31 | Doreen + ASU public affairs | Press release issued through ASU; at least 1 local radio or news feature. | Press release, clipping or recording |  | Not started
V5 | Validation | Night and rough-weather readiness drills | 7 | 8 | 2027-08-31 | Daniel, Lenard | At least 3 drills at night and 2 in moderate sea conditions (only when safe), meeting the same targets as D13. | Drill log |  | Not started
D15 | Validation | Fisher feedback survey 1 | 8 | 8 | 2027-08-31 | Doreen, KC | At least 15 of 20 boats surveyed; top issues logged and assigned. | Survey results |  | Not started
T6 | Training | Joint response exercise with MDRRMO and Coast Guard | 8 | 8 | 2027-08-31 | Lenard, Arnold + MDRRMO | Tabletop and field exercise following the SOP end to end; lessons logged and the SOP updated. | Exercise report |  | Not started
D16 | Year 2 | Year 2 proposal presented to the LGU | 8 | 8 | 2027-08-31 | Doreen, KC + Lenard | Proposal presented while the LGU prepares next year's budget (usually mid-year). | Presentation, meeting notes |  | Not started
V6 | Validation | Mid-pilot validation review | 9 | 9 | 2027-09-30 | Lenard + faculty leader + MDRRMO | M7-M8 results compared with the protocol targets; decisions to keep, adjust or stop recorded. | Review minutes |  | Not started
T7 | Training | Refresher training | 9 | 9 | 2027-09-30 | Doreen, Jade, Arnold | All active fishers and MDRRMO operators refreshed; replacement fishers trained; repeated after any major app update. | Attendance |  | Not started
D17 | Reporting | Actual cost report | 9 | 9 | 2027-09-30 | Doreen + Daniel | Real cost of buoy node, pod and gateway vs budget, with variances explained. | Cost report | Milestone 1 | Not started
R3 | Reporting | Quarterly report 3 | 9 | 9 | 2027-09-30 | Faculty leader, Lenard, Doreen | Technical and financial report submitted to ASU/DOST. | Submitted report |  | Not started
P8c | Promotion | Stakeholder briefing 3 | 9 | 9 | 2027-09-30 | Doreen, Lenard | Mid-pilot results briefing to LGU, MDRRMO, BFAR and Coast Guard. | Attendance, notes |  | Not started
D18 | Validation | Fisher feedback survey 2 | 10 | 10 | 2027-10-31 | Doreen, KC | Same survey repeated; changes since survey 1 reported. | Survey results |  | Not started
V7 | Validation | Usability test round 2 | 10 | 10 | 2027-10-31 | Jade | At least 15 fishers repeat the round 1 tasks; results compared with round 1. | Test sheets, comparison |  | Not started
P7 | Promotion | Fisher stories and documentation | 7 | 11 | 2027-11-30 | Doreen, KC | Monthly photos and video with consent; at least 3 fisher stories published by end of M11. | Published stories |  | Not started
D19 | Validation | Experimental AI evaluation report | 9 | 11 | 2027-11-30 | Lenard | Squall, drift and catch features tested on pilot data; results reported separately from SOS results. | Evaluation report |  | Not started
P9 | Promotion | Outreach to neighbouring LGUs | 10 | 11 | 2027-11-30 | Doreen, KC + Lenard | Pilot results presented to at least 3 other Aklan coastal LGUs; at least 1 LOI (starts the Year 2 pipeline). | Meeting notes, LOIs |  | Not started
D20 | Year 2 | Year 2 commitment from New Washington | 10 | 11 | 2027-11-30 | Doreen, KC | Paid Year 2 agreement or LOI signed. | Signed document | Milestone 1 | Not started
P2 | Promotion | AqOne Facebook page active | 2 | 12 | 2027-12-31 | Doreen, KC | Page live by end of M2; at least 2 posts per week through M12; monthly reach and follower report. | Page link, monthly reports |  | Not started
D14 | Operations | Six-month validation period (supported SOS operation) | 7 | 12 | 2027-12-31 | Daniel (upkeep), Lenard | Every month meets the Monthly Ops targets: uptime, longest outage, drills (including unannounced), inspections, active pods. | 6 monthly ops reports | Milestone 1 | Not started
V4 | Validation | Unannounced drills | 8 | 12 | 2027-12-31 | Lenard + faculty leader | At least 1 unannounced SOS drill per month from M8; MDRRMO acknowledges within 10 minutes in 90%+ of them. | Drill log with timestamps |  | Not started
T8 | Training | Maintenance training for LGU technicians | 11 | 12 | 2027-12-31 | Daniel | At least 2 LGU technicians can check health, swap a pod battery and reseal an enclosure unaided. | Competency checklist |  | Not started
D21 | Operations | Handover package | 12 | 12 | 2027-12-31 | Daniel, Arnold + all | Operations manual handed over; MDRRMO and LGU operators trained; plan agreed for who runs AqOne after Year 1. | Manual, handover record |  | Not started
P10 | Promotion | Pilot results forum | 12 | 12 | 2027-12-31 | Doreen, KC + all | Public presentation of pilot results to stakeholders and the community. | Program, attendance |  | Not started
V8 | Validation | Final validation report | 12 | 12 | 2027-12-31 | Lenard + faculty leader | All protocol metrics vs targets with raw data and limitations; feeds the final report. | Validation report |  | Not started
T9 | Training | Training evaluation report | 12 | 12 | 2027-12-31 | Doreen | Attendance, pre/post test results, competency pass rates and feedback for every training. | Evaluation report |  | Not started
D22 | Reporting | Final report and dataset | 12 | 12 | 2027-12-31 | All + faculty leader | Final technical report, anonymized dataset and final drill results submitted. | Final report, dataset |  | Not started
D23 | Promotion | Conference abstract | 12 | 12 | 2027-12-31 | Lenard + faculty leader | Abstract submitted to one national research forum. | Submission receipt |  | Not started
R4 | Reporting | Quarterly report 4 | 12 | 12 | 2027-12-31 | Faculty leader, Lenard, Doreen | Technical and financial report submitted; terminal report and liquidation follow per DOST rules. | Submitted report |  | Not started
P8d | Promotion | Stakeholder briefing 4 | 12 | 12 | 2027-12-31 | Doreen, Lenard | Final results briefing to LGU, MDRRMO, BFAR and Coast Guard. | Attendance, notes |  | Not started
|  | Progress | 0 of 57 done
Formulas:
Due date = EOMONTH(Overview!$C8,[Due (M)]-1)

## Calendar
Week-by-Week Calendar
Month names follow the start date on the Overview sheet. Shaded rows mark alternate months.
Month | Month name | Week | Activity | Owner | Deliverables
M1 | Jan 2027 | 1 | Kickoff with the faculty project leader and ASU Research Office; confirm expense, procurement, reimbursement and meal rules; assign owners. | All
M1 | Jan 2027 | 1 | Move the backend to paid Render; staging copy, uptime monitoring and a backup restore test. | Lenard | D1
M1 | Jan 2027 | 2 | Get quotations for all hardware and submit purchase requests. | Daniel + faculty leader | D2
M1 | Jan 2027 | 2 | Courtesy visit to New Washington LGU and MDRRMO; present the project; hand over a draft MOA. | Doreen, KC + faculty leader | D4
M1 | Jan 2027 | 3 | Start porting firmware to RAK boards on dev kits. Plan app and dashboard sprints. | Daniel, Jade, Arnold | D5, D6, D7
M1 | Jan 2027 | 3-4 | Communication kit: key messages in 3 languages, brand assets, photo/video consent form, one-page explainer. | Doreen | P1
M1 | Jan 2027 | 4 | Draft the fisher consent form and privacy notice (Data Privacy Act). | Doreen | D3
M2 | Feb 2027 | 1 | Launch the AqOne Facebook page and a 2-posts-per-week content calendar. | Doreen, KC | P2
M2 | Feb 2027 | 1-2 | Firmware port continues; first parts arrive; dashboard SOS acknowledgement flow; app pod pairing. | Daniel, Arnold, Jade | D5, D6, D7
M2 | Feb 2027 | 2 | Draft the validation protocol: metrics, targets, sample sizes, data handling. | Lenard + faculty leader | V1
M2 | Feb 2027 | 3 | With the LGU: pick 2 rooftop gateway sites and 3 host buoys; meet the fisherfolk association. | Doreen, KC, Daniel | D4
M2 | Feb 2027 | 4 | MOA/LOI signed. Gate G1 go/no-go; switch to plan B if no agreement. Chase late parts. | Faculty leader, Doreen | D4
M3 | Mar 2027 | 1-2 | Assemble 22 pods, 2 gateways and 3 buoy nodes; bench SOS tests; pod battery endurance test. | Daniel + all | D5, D8
M3 | Mar 2027 | 2-3 | Barangay assemblies 1 and 2 with the LGU: explain AqOne, sign up boats, collect questions. | Doreen, KC | P3
M3 | Mar 2027 | 3 | 72-hour burn-in and splash tests; app closed testing on 5 phones; MDRRMO operator accounts. Validation protocol approved. | Daniel, Jade, Arnold, faculty leader | D6, D7, D8, V1
M3 | Mar 2027 | 4 | Quarterly report 1; stakeholder briefing 1 (LGU, MDRRMO, BFAR, Coast Guard). | All + faculty leader | R1, P8a
M4 | Apr 2027 | 1-2 | Coverage survey by boat: signal at 50+ GPS-tagged points. | Daniel, Lenard | D9
M4 | Apr 2027 | 2 | Barangay assemblies 3 and 4; 20 boats signed up plus a waitlist. | Doreen, KC | P3
M4 | Apr 2027 | 3 | Coverage map; confirm buoy positions and permits with the LGU and Coast Guard. | Lenard, Doreen | D9
M4 | Apr 2027 | 3-4 | Write the training curriculum, trainer guide, pre/post tests and competency checklist; draft fisher materials in Aklanon. | Doreen, Jade | T1, D10
M4 | Apr 2027 | 4 | Draft the SOS response SOP with MDRRMO and the Coast Guard. | Lenard + faculty leader | T2
M5 | May 2027 | 1 | Install both gateways on the rooftops. | Daniel + all | D11
M5 | May 2027 | 2 | MDRRMO head signs off the SOP. | Lenard + faculty leader | T2
M5 | May 2027 | 2-3 | Install the 3 buoy nodes on host buoys (sea trips). | Daniel + all | D11
M5 | May 2027 | 3 | Print and place IEC materials: tarpaulins at the fish landing, port, barangay halls, MDRRMO; flyers. | Doreen, KC | P4
M5 | May 2027 | 4 | 7-day health check of all installed devices; fisherfolk association reviews training materials; finalize curriculum. | Lenard, Doreen, Jade | D10, D11, T1
M6 | Jun 2027 | 1 | MDRRMO operator training (full day). Champion fisher training (5 fishers). Soft launch with the 5 champion boats. | Arnold, Lenard, Doreen, Jade, Daniel | T3, T4, V2
M6 | Jun 2027 | 1-2 | Usability test round 1 with 10+ fishers. | Jade | V3
M6 | Jun 2027 | 2-3 | Fisher training batches 1-3 with champion helpers; competency check; pods handed over; consent forms signed. | Doreen, KC, Jade + champions | T5, D12
M6 | Jun 2027 | 3 | SOS acceptance test: 30+ drills at 3+ locations; gateway power-loss and carrier-loss tests. | Lenard, Daniel + MDRRMO | D13
M6 | Jun 2027 | 4 | Gate G2 go-live decision. Quarterly report 2, mid-year review, stakeholder briefing 2. | All + faculty leader | R2, P8b
M7 | Jul 2027 | 1 | Community launch and demo day with LGU, MDRRMO, Coast Guard, BFAR and ASU; live SOS demo. | Doreen, KC + LGU | P5
M7 | Jul 2027 | 1-2 | Press release through ASU; local radio or news feature. | Doreen + ASU public affairs | P6
M7 | Jul 2027 | 2-4 | Validation period begins: weekly check-ins, night and rough-weather drills (when safe), experimental AI data collection. | Lenard, Daniel | D14, V5, D19
M7 | Jul 2027 | Monthly | Every month M7-M12: 5+ SOS drills, 1 inspection trip (plus checks after bad weather), uptime report, incident log, 2 Facebook posts per week, photos and video with consent. | Daniel, Lenard, Doreen | D14, P2, P7
M8 | Aug 2027 | 1 | First unannounced drill (then at least 1 per month to M12). | Lenard + faculty leader | V4
M8 | Aug 2027 | 1-2 | Fisher feedback survey 1; app and firmware fixes from the results. Finish night and rough-weather drills. | Doreen, KC, Jade, Daniel | D15, V5
M8 | Aug 2027 | 2 | Joint response exercise with MDRRMO and the Coast Guard (tabletop and field); update the SOP. | Lenard, Arnold + MDRRMO | T6
M8 | Aug 2027 | 3-4 | Present the Year 2 proposal to the LGU during its budget preparation. | Doreen, KC + Lenard | D16
M9 | Sep 2027 | 1 | Mid-pilot validation review against the protocol; keep, adjust or stop decisions. | Lenard + faculty leader + MDRRMO | V6
M9 | Sep 2027 | 2 | Refresher training for fishers and MDRRMO operators; train any replacement fishers. | Doreen, Jade, Arnold | T7
M9 | Sep 2027 | 1-3 | Compile the real cost of each device vs budget. | Doreen, Daniel | D17
M9 | Sep 2027 | 4 | Quarterly report 3; stakeholder briefing 3. | All + faculty leader | R3, P8c
M10 | Oct 2027 | 1-2 | Fisher feedback survey 2; usability test round 2 with 15+ fishers. | Doreen, KC, Jade | D18, V7
M10 | Oct 2027 | 3-4 | Present pilot results to 3+ neighbouring Aklan coastal LGUs; aim for at least 1 LOI. | Doreen, KC + Lenard | P9
M10 | Oct 2027 | 3-4 | Analyze the experimental AI features; draft the Year 2 agreement with the LGU. | Lenard, Doreen | D19, D20
M11 | Nov 2027 | 1-2 | Finish the AI evaluation report (separate from SOS results). | Lenard | D19
M11 | Nov 2027 | 2-4 | Maintenance training for 2+ LGU technicians begins. | Daniel | T8
M11 | Nov 2027 | 3-4 | Year 2 agreement or LOI signed; draft the operations manual; publish the third fisher story. | Doreen, KC, Daniel | D20, D21, P7
M12 | Dec 2027 | 1-2 | Complete technician and operator training; hand over the operations manual; agree who runs AqOne after Year 1. | Daniel, Arnold + all | T8, D21
M12 | Dec 2027 | 2 | Pilot results forum for stakeholders and the community. | Doreen, KC + all | P10
M12 | Dec 2027 | 3 | Final drills; freeze and anonymize the dataset; final validation report; training evaluation report. | Lenard, Daniel, Doreen | V8, T9, D22
M12 | Dec 2027 | 4 | Final report, conference abstract, quarterly report 4, stakeholder briefing 4. Investor Milestone 1 check. | All + faculty leader | D22, D23, R4, P8d

## Gantt
12-Month Gantt
Bars show when each deliverable is worked on. Change Start/End months to move a bar.
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Workstream | Deliverable | Start | End | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Setup | D2 All pilot hardware ordered | 1 | 1 | bar: Jan
| D3 Fisher consent form and privacy notice | 1 | 1 | bar: Jan
| D4 LGU agreement and MDRRMO commitment | 1 | 2 | bar: Jan to Feb
Build | D1 Backend moved to paid Render plan | 1 | 1 | bar: Jan
| D5 Firmware running on RAK boards | 1 | 3 | bar: Jan to Mar
| D6 Android app ready (Google Play closed testing) | 1 | 3 | bar: Jan to Mar
| D7 MDRRMO dashboard ready | 1 | 3 | bar: Jan to Mar
| D8 All devices assembled and bench-tested | 2 | 3 | bar: Feb to Mar
Deploy | D11 Gateways and buoy nodes installed | 5 | 5 | bar: May
| D12 20 boats onboarded | 6 | 6 | bar: Jun
Validation | V1 Validation protocol approved | 2 | 3 | bar: Feb to Mar
| D9 Coverage map | 4 | 4 | bar: Apr
| V2 Soft launch with 5 champion boats | 6 | 6 | bar: Jun
| V3 Usability test round 1 | 6 | 6 | bar: Jun
| D13 SOS acceptance test passed (go-live) | 6 | 6 | bar: Jun
| V5 Night and rough-weather readiness drills | 7 | 8 | bar: Jul to Aug
| D15 Fisher feedback survey 1 | 8 | 8 | bar: Aug
| V4 Unannounced drills | 8 | 12 | bar: Aug to Dec
| V6 Mid-pilot validation review | 9 | 9 | bar: Sep
| D19 Experimental AI evaluation report | 9 | 11 | bar: Sep to Nov
| D18 Fisher feedback survey 2 | 10 | 10 | bar: Oct
| V7 Usability test round 2 | 10 | 10 | bar: Oct
| V8 Final validation report | 12 | 12 | bar: Dec
Training | T1 Training curriculum and trainer guide | 4 | 5 | bar: Apr to May
| D10 Fisher training materials in Aklanon | 4 | 5 | bar: Apr to May
| T2 SOS response procedure (SOP) signed with MDRRMO | 4 | 5 | bar: Apr to May
| T3 MDRRMO operator training | 6 | 6 | bar: Jun
| T4 Champion fisher training | 6 | 6 | bar: Jun
| T5 Fisher training batches and competency check | 6 | 6 | bar: Jun
| T6 Joint response exercise with MDRRMO and Coast Guard | 8 | 8 | bar: Aug
| T7 Refresher training | 9 | 9 | bar: Sep
| T8 Maintenance training for LGU technicians | 11 | 12 | bar: Nov to Dec
| T9 Training evaluation report | 12 | 12 | bar: Dec
Promotion | P1 Communication kit | 1 | 2 | bar: Jan to Feb
| P2 AqOne Facebook page active | 2 | 12 | bar: Feb to Dec
| P8a Stakeholder briefing 1 | 3 | 3 | bar: Mar
| P3 Barangay assemblies in coastal barangays | 3 | 4 | bar: Mar to Apr
| P4 IEC materials printed and placed | 5 | 5 | bar: May
| P8b Stakeholder briefing 2 | 6 | 6 | bar: Jun
| P5 Community launch and demo day | 7 | 7 | bar: Jul
| P6 Local media feature | 7 | 8 | bar: Jul to Aug
| P7 Fisher stories and documentation | 7 | 11 | bar: Jul to Nov
| P8c Stakeholder briefing 3 | 9 | 9 | bar: Sep
| P9 Outreach to neighbouring LGUs | 10 | 11 | bar: Oct to Nov
| P10 Pilot results forum | 12 | 12 | bar: Dec
| D23 Conference abstract | 12 | 12 | bar: Dec
| P8d Stakeholder briefing 4 | 12 | 12 | bar: Dec
Operations | D14 Six-month validation period (supported SOS operation) | 7 | 12 | bar: Jul to Dec
| D21 Handover package | 12 | 12 | bar: Dec
Reporting | R1 Quarterly report 1 | 3 | 3 | bar: Mar
| R2 Quarterly report 2 and mid-year review | 6 | 6 | bar: Jun
| D17 Actual cost report | 9 | 9 | bar: Sep
| R3 Quarterly report 3 | 9 | 9 | bar: Sep
| D22 Final report and dataset | 12 | 12 | bar: Dec
| R4 Quarterly report 4 | 12 | 12 | bar: Dec
Year 2 | D16 Year 2 proposal presented to the LGU | 8 | 8 | bar: Aug
| D20 Year 2 commitment from New Washington | 10 | 11 | bar: Oct to Nov
| Gates (see Gates sheet) |  |  | Feb: ▲ G1; Jun: ▲ G2; Dec: ▲ G3

## Training Plan
Training Plan: Fishers, MDRRMO and LGU
Every session with its audience, length, topics, trainer, timing and how we check that people learned.
ID | Session | Audience and size | Length | Topics | Trainer | When | How we check learning
T2 | SOS response SOP workshop | MDRRMO head and duty officers, Coast Guard and BFAR focal persons (6-10) | Half day | Who receives and acknowledges an SOS; target times (acknowledge within 10 min); escalation to Coast Guard and BFAR; contact tree; what to tell families; record keeping. | Lenard + faculty leader | M5 (May) | SOP signed by the MDRRMO head
T3 | MDRRMO operator training | All operators on the duty rota (at least 4) | 1 day (6 h) | Dashboard log-in and roles; reading SOS alerts, boat position and drift; acknowledging; following the SOP; device health; what to do when the system is down; practice with live test SOS. | Arnold, Lenard | M6 (Jun) | Each operator acknowledges a test SOS within 2 min; post-test 80%+
T4 | Champion fisher training | 5 respected fishers chosen with the fisherfolk association | Half day + 1 week soft launch | Everything in T5, plus how to help other fishers, how to report problems, basic troubleshooting. | Doreen, Jade, Daniel | M6 (Jun) | Competency checklist passed; can demonstrate to a peer
T5 | Fisher training batches (3) | 20 boats, 1-2 fishers per boat (about 12-15 people per batch); family members welcome | Half day each: 2 h classroom + 1 h practice at the shore | What AqOne does and does not do; pairing phone and pod; sending SOS (app and pod button); what happens after an SOS; charging and battery level; strapping the pod; care and basic checks; privacy and consent; safety at sea reminders. | Doreen, KC, Jade + champions | M6 (Jun) | Every fisher sends an SOS and charges a pod unaided before receiving a pod; pre/post test
T6 | Joint response exercise | MDRRMO, Coast Guard, BFAR, 5 champion fishers | 1 day | Tabletop walk-through of the SOP, then a field drill: a champion boat sends SOS, MDRRMO acknowledges, Coast Guard responds; debrief. | Lenard, Arnold + MDRRMO | M8 (Aug) | SOP followed end to end; lessons logged; SOP updated
T7 | Refresher training | All active fishers and MDRRMO operators; replacement fishers | 2 h per group | Common mistakes found in the first 2 months; new app features; survey feedback; repeat practice SOS. | Doreen, Jade, Arnold | M9 (Sep) | Attendance; practice SOS by each participant
T8 | LGU technician maintenance training | At least 2 LGU technicians | 2 days | Health dashboard; inspection checklist; swapping pod batteries; resealing enclosures; replacing antennas and arrestors; safety at height and at sea. | Daniel | M12 (Dec) | Each technician completes the tasks unaided
T9 | Training evaluation | All trainings above | - | Attendance, pre/post tests, competency pass rates, participant feedback, improvements for Year 2. | Doreen | M12 (Dec) | Training evaluation report
Training rules: materials in Aklanon first; sessions near the fish landing at times that avoid fishing hours; no fisher receives a pod before passing the competency check; attendance and consent recorded for every session.

## Validation Plan
Validation Plan
What we measure to prove AqOne works, how, with how many, and what counts as a pass. The validation period is months 7-12; earlier items prove readiness.
ID | Test | What we measure | Method | Sample | Pass target | When | Owner
V1 | Validation protocol | Defines every test below, data handling and consent | Written protocol reviewed by the faculty leader | - | Approved before any field test | M3 (Mar) | Lenard
D5 | Bench SOS test | End-to-end delivery pod → gateway → dashboard; pod battery life | Scripted test in the lab | 100 messages; 3 pods for battery | 100/100 delivered; battery 48 h+ | M3 (Mar) | Daniel
D9 | Coverage survey | LoRa signal strength and delivery by location | Boat runs with a test pod; GPS-tagged readings | 50+ points | Coverage map; buoy positions confirmed | M4 (Apr) | Daniel, Lenard
V2 | Soft launch | Real-world use on 5 boats before full rollout | 5 champion boats for 1 week | 5 boats, 10+ messages each | All messages delivered or issues logged and fixed | M6 (Jun) | Lenard, Daniel
V3 | Usability test round 1 | Can fishers use it without help? | Observed tasks: pair, send SOS, check battery | 10+ fishers | 90%+ complete each task; SOS within 60 s | M6 (Jun) | Jade
D13 | SOS acceptance test | Delivery, speed, acknowledgement, failure handling | Scheduled drills at 3+ locations; power and carrier cut tests | 30+ drills | 95%+ within 2 min; acknowledged within 10 min; failure tests passed | M6 (Jun) | Lenard, Daniel
D14 | Six-month operation | Uptime, outages, drills, inspections, active pods | Monthly Ops sheet | 6 months | All 6 months PASS | M12 (Dec) | Daniel, Lenard
V4 | Unannounced drills | Real response when MDRRMO does not know it is a drill | Faculty leader triggers a drill at a random time | 1+ per month, M8-M12 | Acknowledged within 10 min in 90%+ | M12 (Dec) | Lenard + faculty leader
V5 | Night and rough-weather drills | Performance in harder conditions | Drills at night and in moderate seas, only when safe | 3 night + 2 rough | Same targets as D13 | M8 (Aug) | Daniel, Lenard
D15/D18 | Fisher feedback surveys | Satisfaction, trust, problems, suggestions | Short survey in Aklanon | 15+ boats each round | Top issues logged and acted on | M10 (Oct) | Doreen, KC
V6 | Mid-pilot review | Are we on track against the protocol? | Review meeting with ASU and MDRRMO | M7-M8 data | Decisions recorded | M9 (Sep) | Lenard
V7 | Usability test round 2 | Improvement since round 1 | Repeat round 1 tasks | 15+ fishers | Equal or better than round 1 | M10 (Oct) | Jade
D19 | Experimental AI evaluation | Squall, drift and catch features on pilot data | Compare predictions with observed events | All pilot data | Reported separately; no SOS claims depend on it | M11 (Nov) | Lenard
V8 | Final validation report | All results vs targets | Compile raw data and results | Whole pilot | Complete report with limitations | M12 (Dec) | Lenard + faculty leader
Yellow test names fall inside the validation period (months 7-12). Every result goes into the final validation report (V8), including failures.

## Promotion Plan
Promotion Plan
How we build awareness and trust in New Washington and prepare Year 2 customers.
ID | Activity | Channel | Audience | When | Owner | Target (KPI)
P1 | Communication kit | Internal | Team, partners | M1-M2 | Doreen | Key messages in 3 languages; consent form for photos
P2 | AqOne Facebook page | Facebook (main channel) | Fishers' families, community, LGUs | M2-M12 | Doreen, KC | 2+ posts per week; monthly reach report
P3 | Barangay assemblies | Face to face with LGU | Fishers in coastal barangays | M3-M4 | Doreen, KC + LGU | 4+ assemblies; 20 boats signed up + waitlist
P4 | IEC materials | Tarpaulins, flyers (Aklanon) | Fishers, port users, barangay halls | M5 | Doreen, KC | Tarps placed at 4+ sites; flyers at every assembly
P5 | Community launch and demo day | Public event | Community, LGU, MDRRMO, Coast Guard, BFAR, ASU | M7 | Doreen, KC + LGU | 60+ attendees; live SOS demo
P6 | Local media | Press release, local radio | Aklan public | M7-M8 | Doreen + ASU public affairs | 1+ feature
P7 | Fisher stories | Facebook, reports | Community, investors, DOST | M7-M11 | Doreen, KC | 3+ stories with consent
P8 | Stakeholder briefings (4) | Meetings | LGU, MDRRMO, BFAR, Coast Guard | M3, M6, M9, M12 | Doreen, Lenard | Attendance and commitments recorded
P9 | Neighbouring LGU outreach | Presentations | 3+ Aklan coastal LGUs | M10-M11 | Doreen, KC + Lenard | 1+ LOI (Year 2 pipeline)
P10 | Pilot results forum | Public event | Stakeholders, community | M12 | Doreen, KC + all | Results presented; Year 2 partners invited
D23 | Conference abstract | National research forum | Researchers, DOST | M12 | Lenard + faculty leader | Abstract submitted
Promotion rules: never show a fisher's face, name or boat without signed consent; never promise coverage we have not measured; sponsor logos (Year 2) never appear on SOS or alert screens.

## Monthly Ops
Validation Period Tracker (Months 7-12)
Type the actual numbers each month in the yellow cells. A month passes when every target is met.
TARGETS (change here if ASU or MDRRMO agree different ones)
Network uptime (minimum) |  |  | 95%
Longest outage (max. hours) |  |  | 6
SOS drills (min. per month) |  |  | 5
Unannounced drills (min., from M8) |  |  | 1
Inspection trips (min. per month) |  |  | 1
Pods used on trips (min., of 20) |  |  | 15
Month | Month name | Uptime | Longest outage (h) | SOS drills | Unannounced drills | Inspection trips | Pods used on trips | Result | Incidents and notes
M7 | Jul 2027 | [6 empty] | Pending
M8 | Aug 2027 | [6 empty] | Pending
M9 | Sep 2027 | [6 empty] | Pending
M10 | Oct 2027 | [6 empty] | Pending
M11 | Nov 2027 | [6 empty] | Pending
M12 | Dec 2027 | [6 empty] | Pending
Months passed |  | 0 of 6 | [6 empty] | D14 is met when all 6 months pass. In M7, unannounced drills are not yet required.

## Gates
Gates and Investor Milestone 1
Each gate lists the deliverables it needs. Status is read from the Deliverables sheet.
G1 Go/no-go on LGU agreement
Deadline | 2027-02-28
Needs deliverable | ID | Due date | Status | Pass/fail test
LGU agreement and MDRRMO commitment | D4 | 2027-02-28 | Not started | Signed MOA or LOI covering host buoys, boat access, 2 gateway sites and permits; MDRRMO agrees to monitor alerts and run drills.
Gate result |  |  | NOT YET | If not met: switch to plan B (ASU-arranged boats, buoys and gateway sites) before installation.
G2 Go-live
Deadline | 2027-06-30
Needs deliverable | ID | Due date | Status | Pass/fail test
SOS response procedure (SOP) signed with MDRRMO | T2 | 2027-05-31 | Not started | Written SOP: who acknowledges an SOS, target times, escalation to Coast Guard and BFAR, contact tree; signed off by the MDRRMO head.
MDRRMO operator training | T3 | 2027-06-30 | Not started | All operators on the duty rota (at least 4) trained; each acknowledges a test SOS on the dashboard within 2 minutes; post-test score 80% or higher.
Fisher training batches and competency check | T5 | 2027-06-30 | Not started | 3 batches covering all 20 boats (1-2 fishers per boat). Every fisher sends an SOS and charges a pod without help before receiving a pod; pre/post test gain recorded.
20 boats onboarded | D12 | 2027-06-30 | Not started | 20 boats have pods; consent forms signed; pod serial numbers matched to boats in the dashboard.
SOS acceptance test passed (go-live) | D13 | 2027-06-30 | Not started | At least 30 drills at 3+ locations; 95%+ reach the dashboard within 2 min; MDRRMO acknowledges within 10 min; gateway power-loss and carrier-loss tests passed.
Gate result |  |  | NOT YET | If not met: do not go live; fix, re-test within 4 weeks.
G3 Investor Milestone 1 (unlocks ₱3M)
Deadline | 2027-12-31
Needs deliverable | ID | Due date | Status | Pass/fail test
SOS acceptance test passed (go-live) | D13 | 2027-06-30 | Not started | At least 30 drills at 3+ locations; 95%+ reach the dashboard within 2 min; MDRRMO acknowledges within 10 min; gateway power-loss and carrier-loss tests passed.
Six-month validation period (supported SOS operation) | D14 | 2027-12-31 | Not started | Every month meets the Monthly Ops targets: uptime, longest outage, drills (including unannounced), inspections, active pods.
Actual cost report | D17 | 2027-09-30 | Not started | Real cost of buoy node, pod and gateway vs budget, with variances explained.
Year 2 commitment from New Washington | D20 | 2027-11-30 | Not started | Paid Year 2 agreement or LOI signed.
Gate result |  |  | NOT YET | If not met: the investor may decline tranche 1. Proof: DOST/ASU reports, dashboard logs, signed Year 2 document.
Investor Milestone 2 (end of Year 2, unlocks ₱5M): 3 paying municipalities, 150+ active pods, 1+ co-op purchase agreement, pilot LGU renews, deployment gross margin 35%+. P9 (neighbouring LGU outreach) starts that pipeline.
Formulas:
Due date = INDEX(Deliverables!$F5:F61,MATCH([ID],Deliverables!$A5:A61,0))

## Budget Notes
Budget Notes: Costs This Plan Adds
The current budget has only ₱8,000 for outreach (B.6). These promotion and training costs are estimates and are NOT yet in Aquanons_Master_Budget.xlsx. Decide with ASU which to add.
For | Item | Qty | Unit cost | Total | Basis
T4, T5 | Fisher training snacks and meals | 50 | 150 | 7500 | About 45 fishers in 3 batches + 5 champions (estimate)
T7 | Refresher training snacks | 40 | 150 | 6000 | Fishers and operators (estimate)
T2, T3, T6 | MDRRMO workshops and joint exercise snacks | 30 | 150 | 4500 | SOP workshop, operator training, joint exercise (estimate)
T1, D10 | Printed training handouts and picture guides | 60 | 50 | 3000 | One per trained person plus spares (estimate)
P3 | Barangay assembly snacks | 120 | 60 | 7200 | 4 assemblies × about 30 people (estimate)
P4 | Tarpaulins | 6 | 800 | 4800 | Fish landing, port, barangay halls, MDRRMO (estimate)
P4 | Flyers in Aklanon | 500 | 6 | 3000 | Estimate
P5 | Launch and demo day snacks | 60 | 150 | 9000 | Venue from the LGU in kind (estimate)
P5 | Launch tarpaulin and program printing | 1 | 2000 | 2000 | Estimate
P10 | Results forum snacks | 40 | 150 | 6000 | Estimate
P9 | Travel to 3 neighbouring LGUs | 3 | 1500 | 4500 | Public transport rate for a small team (estimate)
P2 | Facebook post boosting | 10 | 500 | 5000 | ₱500/month M3-M12; CONFIRM DOST allows paid promotion (estimate)
| Total added by this plan |  |  | 62500
| Already in the budget (B.6 pilot community outreach) |  |  | 8000
| Extra needed beyond the current budget |  |  | 54500
Confirm with ASU: whether meals and snacks for trainings are allowed and at what rate, and whether paid social media promotion is an eligible expense. Adding the extra amount raises the grant request (plus 5% contingency if allowed).